## Task List
Feature | Tasks | Priority | Difficulty | Time Estimate (in hours) | Notes
General R&D | Become familiar with the OGRE engine | 1 | 1 | 40
| Learn how to use Bullet Physics | 1 | 1 | 40
Physics | Calculate bounding box for models | 3 | 3 | 1
| Determine collision between models | 4 | 3 | 5
| Determine collision between models and world | 3 | 3 | 5
Enemy | Create enemy object | 1 | 4 | 5 | Create enemy classes
| Implement enemy modles | 1 | 3 | 10
| Create movement state | 2 | 5 | 20 | Implement movement logic for enemies (default enemy state)
| Create death state | 4 | 5 | 1 | Implement death logic for enemies
| Calculate radii for support enemies | 3 | 4 | 5
| Create enemy waves | 3 | 5 | 10 | Determine since, number, and timing of enemy waves
Tower | Create tower object | 1 | 4 | 5 | Create tower classes
| Implement tower models | 1 | 3 | 10
| Calculate attack radii for different tower types | 2 | 3 | 10
| Create idle state | 4 | 5 | 5 | Implement logic towers will use to scan for enemies (default tower state)
| Create attack state | 3 | 5 | 20 | Implement logic on how towers will attack when enemy is in range
Player Character | Create player object | 1 | 4 | 5 | Create player class
| Implement player model | 1 | 3 | 10
| Implement resource gathering logic | 2 | 3 | 5
| Implement tower building, upgrading, and salvaging logic | 2 | 3 | 5
| Able to increase movement speed | 5 | 5 | 1
| Able to increase harvest rate | 5 | 5 | 1
| Able to increase build speed | 5 | 5 | 1
| Able to increase upgrade speed | 5 | 5 | 1
| Create knockdown state | 5 | 5 | 5 | Implement logic for when an enemy knocks down the player
| Create invulnerable state | 5 | 5 | 1 | Implement logic for when the player becomes invulnerable to enemy collisions
Villager | Create villager object | 2 | 4 | 3 | Create villager class
| Implement villager models | 2 | 3 | 10
| Create movement state | 4 | 5 | 5 | Implement movement logic for villagers
Resource | Create resource object | 1 | 4 | 3 | Create resource classes
| Implement resource models | 1 | 3 | 10
Event Managment | Create Event Manager Class | 2 | 3 | 15 | Create base class and implement functionality for adding and removing subscribers and adding, broadcasting, and clearing events
| Create Event Class | 2 | 4 | 10
Animations | Implement player movement animation | 2 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement enemy movement animation | 2 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement villager movement animation | 3 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement tower attack animations | 2 | 3 | 40 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement tower build animation | 3 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement tower upgrade animation | 4 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement resource depletion animation | 5 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement enemy support animation | 5 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement enemy death animation | 5 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement player harvest animation | 4 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
| Implement player knockdown animation | 5 | 3 | 20 | Convert model animation data into a format that OGRE understands (this requires out models to have baked in animations)
3d Models | Find free 3D models which have animations | 1 | 5 | 10
Camera | Create camera object | 1 | 4 | 1 | Position and lock camera object at a specified height and angle
| Add a zoomed state to the camera | 5 | 4 | 5
A.I. | Create algorithms for path finding | 1 | 2 | 30 | This will serve as main portion of the logic for enemies and villagers who travel based on shortest path. This will also include path finding for player movement.
World | Generate Terrain based on height map | 1 | 1 | 72 | Create an algorithm which will take a level description and then generate the terrain algorithmically as opposed to manually.
| Create algorithm for procedurally generating textures | 1 | 1 | 96 | Use level data to generate the corresponding textures to the level
| Create level designs | 1 | 5 | 10
| Create XML files for level designs | 1 | 5 | 5
| Parse level data from XML files | 1 | 4 | 10
| Create levels | 1 | 3 | 20 | Create levels which contain data that will be used in terrain generation
Lighting | Create a global lighting object | 1 | 3 | 1
| Create day and night lighting states | 5 | 5 | 5
| Determine player shading | 3 | 4 | 40
| Determine tower shading | 3 | 4 | 40
| Determine enemy shading | 3 | 4 | 10 | Time estimate lower since most of the work was already done for player character shading
| Determine villager shading | 3 | 4 | 10 | Time estimate lower since most of the work was already done for player character shading
| Determine environment shading | 2 | 3 | 40
| Add shadows | 4 | 3 | 10
Particle Effects | Learning the OGRE particlel system | 2 | 1 | 10
| Create fire effects | 3 | 1 | 20 | Create a particle emitter and particle behaviour patterns(spawn rate, velocity, color, etc.) to simulate fire
| Add hooks in game for fire effect(s) | 3 | 3 | 10
| Create explosion effects | 3 | 1 | 20 | Create a particle emitter and particle behaviour patterns(spawn rate, velocity, color, etc.) to simulate an explosion
| Add hooks in game for explosion effect(s) | 3 | 3 | 10
| Create smoke/fog effects | 5 | 2 | 20 | Create a particle emitter and particle behaviour patterns(spawn rate, velocity, color, etc.) to simulate smoke/fog
| Add hooks in game for smoke/fog effect(s) | 5 | 3 | 10
| Add hooks for miscellaneous effect(s) | 3 | 3 | 10
Input | Implement keyboard and mouse controls | 1 | 3 | 20
User Interface | Create main menu | 5 | 5 | 10
| Create pause menu | 5 | 5 | 10
| Create in game HUD | 3 | 4 | 20
| Create tower menu (salvage, upgrade, etc.) | 3 | 5 | 10
| Create build menu | 3 | 5 | 10
| Create player customization menu | 5 | 5 | 10
| Research UI implementations for OGRE | 2 | 5 | 5
Audio | Gather free music and sound effects | 4 | 5 | 5
| Implement in game music | 5 | 5 | 5
| Implement in game sound effects | 3 | 4 | 15
| Implement menu music | 5 | 5 | 2
Debug | Create a debug menu | 2 | 4 | 10
Testing | Fix Bugs & Balancing | 1 | 1 | 750
Extra Features | Add extra features listed in GDD | 5 | 3 | 30
1803

## Priority Task List
Tasks | Priority | Difficulty | Time Estimate (in hours)
Generate Terrain based on height map | 1 | 1 | 72
Create algorithm for procedurally generating textures | 1 | 1 | 96
Create camera object | 1 | 4 | 1
Create a global lighting object | 1 | 3 | 5
Create enemy object | 1 | 4 | 5
Create enemy manager | 1 | 4 | 3
Create tower object | 1 | 4 | 5
Create tower manager | 1 | 4 | 3
Create player object | 1 | 4 | 3
Create resource object | 1 | 4 | 3
Create resource manager | 1 | 4 | 3
Create algorithms for path finding | 1 | 2 | 20
Implement keyboard and mouse controls | 1 | 3 | 20
Implement enemy models | 1 | 3 | 10
Implement tower models | 1 | 3 | 10
Implement player model | 1 | 3 | 10
Implement resource models | 1 | 3 | 10
Create XML files for level designs | 1 | 5 | 5
Parse level data from XML files | 1 | 4 | 10
Create Event Manager Class | 2 | 3 | 15
Create Event Class | 2 | 4 | 10
Create villager object | 2 | 4 | 3
Implement villager models | 2 | 3 | 10
Create a debug menu | 2 | 4 | 10
Calculate attack radii for different tower types | 2 | 3 | 10
Implement tower building, upgrading, and salvaging logic | 2 | 3 | 5
Implement resource gathering logic | 2 | 3 | 5
Implement player movement animation | 2 | 3 | 10
Implement enemy movement animation | 2 | 3 | 10
Implement tower attack animations | 2 | 3 | 10
Determine environment shading | 2 | 3 | 20
Create in game HUD | 3 | 4 | 40
Calculate bounding box for models | 3 | 3 | 1
Determine collision between models | 3 | 3 | 20
Determine collision between models and world | 3 | 3 | 30
Create attack state | 3 | 5 | 50
Calculate radii for support enemies | 3 | 4 | 5
Implement tower build animation | 3 | 3 | 20
Implement villager movement animation | 3 | 3 | 20
Determine player shading | 3 | 4 | 40
Determine tower shading | 3 | 4 | 40
Determine enemy shading | 3 | 4 | 10
Determine villager shading | 3 | 4 | 10
Create enemy waves | 3 | 5 | 10
Add hooks in game for fire effect(s) | 3 | 3 | 10
Add hooks in game for explosion effect(s) | 3 | 3 | 10
Add hooks for miscellaneous effect(s) | 3 | 3 | 10
Create fire effects | 3 | 1 | 20
Create explosion effects | 3 | 1 | 20
Create build menu | 3 | 5 | 10
Create tower menu (salvage, upgrade, etc.) | 3 | 5 | 10
Implement in game sound effects | 3 | 4 | 20
Create movement state | 4 | 5 | 5
Create idle state | 4 | 5 | 3
Create death state | 4 | 5 | 1
Implement tower upgrade animation | 4 | 3 | 10
Implement player harvest animation | 4 | 3 | 10
Add shadows | 4 | 3 | 5
Implement enemy support animation | 5 | 3 | 10
Implement resource depletion animation | 5 | 3 | 10
Implement player knockdown animation | 5 | 3 | 20
Implement enemy death animation | 5 | 3 | 20
Add hooks in game for smoke/fog effect(s) | 5 | 3 | 10
Create smoke/fog effects | 5 | 2 | 20
Create knockdown state | 5 | 5 | 5
Create invulnerable state | 5 | 5 | 1
Implement in game music | 5 | 5 | 5
Implement menu music | 5 | 5 | 2
Create pause menu | 5 | 5 | 10
Create main menu | 5 | 5 | 10
Create day and night lighting states | 5 | 5 | 5
Add a zoomed state to the camera | 5 | 4 | 5
Create player customization menu | 5 | 5 | 10
Implement player upgrades | 5 | 5 | 1
Add extra features listed in GDD | 5 | 3 | 30
Task Assignments
Pavel
Terrain Generation & Procedural Textures
Once done pick up tasks based on what is remaining
Pierre
User Interface
Animation
Physics
Event Manager and Events
Keenan
Implement Gameplay Prototype
XML Level Files and Parsing
Particle Effects
Nick
Pathfinding and enemies
Implement Gameplay Prototype
Audio
Animation
684

## New Tasks
Add music | 4 hours
Design second level | 2 hours
Create height map for second level | 3 hours
Create splat map for second level | 2 hours
Create waves for second level | 2 hours
Implement water for second level | 10 hours
Find model for torch tower | 1 hour
Find model for tesla tower | 1 hour
Find model for magic tower | 1 hour
Create new tower classes | 3 hours
Implement new tower models | 2 hours
Create particle effect for torch tower | 3 hours
Calculate point light for torch tower | 3 hours
Create particle effect for tesla tower | 5 hours
Create particle effect for magic tower | 5 hours
Add additional tower sounds | 4 hours
Create day / night cycle | 5 hours
Create fog for night | 10 hours
Implement night mechanics | 5 hours
Find model for Boss enemy | 1 hour
Create boss class
Implement enemy variants | 5 hours
Incorporate boss into new level | 2 hours
Implement player powers | 3 hours
Create any required particle effects for player powers | 5 hours
Find additional player character models | 2 hours
Create character select screen | 5 hours
Implement new character types | 6 hours
Implement newtowrk co-op multiplayer | 30 hours
Testing, balancing,and polish | 160 hours | Will use the last two sprints for this

## Schedule
2013-02-20
Level 1 Done and ready for polish/balance/testing
Complete Shadows
Complete Terrain Randomization
Tower particles done
Sound effects done
UI done
2013-03-13
Lighting Done
Night time game logic done
Boss Done
Player Powers with coresponding effects Done
Enemy variants done
2013-03-27
Extra characters implemented
Level 2 Done and ready for polish/balance/testing
Water Done
Fog effects Done
Begin polish/balancing/testing
2013-04-17
Game Done